Template for Process Action Plan (PAP) for projects up to DKK 10 mill.

| Time line | Programme | Documentation |
| --- | --- | --- |
| Min. 1 month prior to the head of unit’s approval of the project | The project budget is inserted into the proposal for the Finance Act – hearing will be sent out by UGS  (normally in February/March) |  |
|  | Process Action Plan developed | Process Action Plan for project development up to signing of commitments. |
|  | Analysis started (as applicable) |  |
|  | Preparation of Development engagement Document (DED).  Either 1) DED particularly designed for projects below 10 mill. DKK., which includes standard text on financial management, monitoring and evaluation, anti-corruption etc.  Or 2) Standard DED + Agreement with implementing partner |  |
|  | **Internal appraisal**  Use checklist for appraisal for projects up to DKK 10 million | Development engagement Document (below 10 mill. DKK version)  Checklist is signed by the appraising desk officer and management of the MFA unit and attached to the grant documents (DED). |
|  | **Presentation and approval of the head of unit** | Appropriation note filled in + DED |
| Signing of legally binding agreement (commitment) with partner. | Either 1) DED particularly designed for projects below 10 mill. DKK., which includes standard text on financial management, monitoring and evaluation, anti-corruption etc.  Or 2) Standard DED + Agreement with implementing partner |
| Book commitment in MFA’s financial systems within budgeted quarter. |  |